## Sheet1
| Project name: | Online Voting System Using Blockchain
| Project Start: | 2024-07-11
| Current Date: | 2024-08-22
| Weeks in Progress: | 6
[5 empty] | 2024-07-11 | 2024-07-18 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-15 | 2024-08-22 | 2024-08-29 | 2024-09-05 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-03 | 2024-10-10 | 2024-10-17
Task | Start Date | End Date | Days | Progress | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Group Finalization / Domain | 2024-07-11 | 2024-07-17 | 6 | 100%
Topic finalization/Project Name submission (objectives/problem statement/scope) | 2024-07-18 | 2024-07-24 | 6 | 100%
Topic finalization/Project Name submission | 2024-07-25 | 2024-07-31 | 6 | 100%
Literature study and limitation of existing system (refer IEEE/ACM/Springer/Elsevier journal papers) | 2024-08-01 | 2024-08-07 | 6 | 80%
Abstract, Problem statement/scope and objective Finalization. | 2024-08-08 | 2024-08-14 | 6 | 90%
Implementation plan /Timeline chart for sem vii and viii | 2024-08-15 | 2024-08-21 | 6 | 50%
SRS-Functional and Non functional requirements, S/w Engg Model | 2024-08-22 | 2024-08-28 | 6 | 0%
Proposed system architecture/flow chart and Analysis and Design: Use Case, DFD-0,Sequence | 2024-08-29 | 2024-09-04 | 6 | 0%
Review I(on Activity 3 to 8)
Reviw Paper Publication (Survey Paper) | 2024-09-05 | 2024-09-11 | 6 | 0%
Analysis and Design: Data model/data set, Class diagram,Activity diagram, Deployment Diagram | 2024-09-12 | 2024-09-18 | 6 | 0%
Wireframe/Algorithm and flow chart/Input form design/Output Report Design | 2024-09-19 | 2024-09-25 | 6 | 0%
RMMM Plan, Feasibility analysis and Test case Design | 2024-09-26 | 2024-10-02 | 6 | 0%
Review II (on Activity 3 to 13)
Project Report Preparation | 2024-10-03 | 2024-10-09 | 6 | 0%
Finalisation of PPT's nad project report with print and guide signature | 2024-10-10 | 2024-10-16 | 6 | 0%
Note on C3: ATHARVA: Insert Start Date